## Sheet1
Date | Topic | Description
2020-03-25 | Data Update | Libraries must notify CARLI if they are concerned about the Special Collections workflow not meeting their needs for their local data.
2020-04-01 | Data Update | Submit the I-Share Alma Migration Form Update Survey to CARLI.
2020-04-01 | Voyager | Stop adding new locations and vendors to Voyager.
2020-04-01 | Alma | Stop adding new libraries, locations, vendors to Alma test environments.
Wednesday, April 15, 2020 | Data Update | CARLI provides new link resolver spreadsheets to Libraries with non-Ex Libris Link Resolvers (EBSCO, OCLC)
2020-04-22 | Voyager | Last day to file any new Voyager work requests (WROs) for physical or electronic MARC record bulk imports or deletes.
2020-04-22 | Voyager | Last day to file any new Voyager work requests (WROs) for Fiscal Period Close (FPC) (must be run by Friday, April 24.)
2020-04-24 | Voyager | Last day that CARLI will run any Fiscal Period Close (FPC) in Voyager before the Technical Freeze starts May 1.
2020-04-25 | Voyager | Last day that CARLI will run any new or ongoing bibliographic bulk import loads into Voyager.
2020-04-25 | Voyager | Libraries stop adding any new e-resource bibs and holdings in Voyager.
Monday, April 27, 2020 | Data Update | CARLI provides P2E files to Libraries in Box.
2020-04-30 | Voyager | Last day for work in Voyager that will stop during the “Tech Freeze”.
Friday, May 1, 2020 at 12:01am | Voyager | Technical Freeze starts Stop making any manual changes to inventory in Voyager (i.e., stop adding/deleting/editing bibs, MFHDs, items, POs, invoices, serials check-in, etc.), and stop setting “OK to export” to send holdings to OCLC WorldCat.
2020-05-01 | Alma | Alma Configuration Freeze starts Stop making any changes to Alma configuration settings
2020-05-01 | Primo VE/Alma | Stop making configuration changes to Primo VE (in Alma Configuration).
2020-05-01 | Data Update | Libraries return updated P2E files back to CARLI via Box.
2020-05-01 | Link Resolver | Libraries with non-Ex Libris Link Resolvers (EBSCO, OCLC) return draft form to CARLI.
2020-05-04 | Link Resolver | Libraries using Ex Libris 360 products provide draft reports to CARLI.
2020-05-08 | Link Resolver | Libraries stop updating SFX. SFX Freeze begins.
2020-05-08 | Link Resolver | Libraries using Ex Libris 360 products provide final reports to CARLI. 360 Product Freeze begins.
2020-05-11 | Link Resolver | Libraries with non-Ex Libris Link Resolvers (EBSCO, OCLC) return final form to CARLI. Non-Ex Libris Link Resolver Freeze begins.
2020-05-22 | Alma/Primo VE | Stop all Alma and Primo VE demo, testing, and training activities.
2020-06-11 | Voyager | Stop placing UB requests; “request” buttons disabled in VuFind/WebVoyage.
2020-06-15 | Voyager | Last day to file WRO for Patron Purges in Voyager. Last day Patron Purges will be run in Voyager.
2020-06-17 | Voyager | Last day to file WRO for Patron Loads in Voyager. Last day Patron Loads will be run in Voyager.
Thursday, June 18, 2020 at 11:59pm | Voyager | Stop using Voyager Circulation.
Friday, June 19, 2020 at 12:01am | Voyager | Circ Freeze Starts Stop making any manual changes to patron records and circ status (adding/deleting/editing records, fines/fees, circ status).
Friday, June 19 - Wednesday, June 24, 2020 | Alma | I-Share libraries MAY opt to use Alma offline circ.
2020-06-24 | Alma/Primo VE | Go Live! All Activities Live in Alma and PrimoVE.